## Sheet1
sno | date | task | status
1 | 2019-05-08 | Android studio, sdk, and JDK installation | completed
2 | 2019-05-09 | Intriduction about android, sample app development | completed
3 | 2019-05-10 | project requirements gathering and understanding | completed
4 | 2019-05-11 | Saturday | holiday for him
5 | 2019-05-12 | Sunday | holiday for him
6 | 2019-05-13 | analysis and working on views(xml) | completed
7 | 2019-05-14 | design created for project | completed
8 | 2019-05-15 | design created for project | completed
9 | 2019-05-16 | training on volley library and web services | completed
10 | 2019-05-17 | training on recycler view with adapters and practise | completed
11 | 2019-05-18 | Saturday | holiday for him
12 | 2019-05-19 | Sunday | holiday for him
13 | 2019-05-20 | implementation of splash screen and home page | completed
14 | 2019-05-21 | Training on Intents and menus and practise | completed
15 | 2019-05-22 | Login and register page of volunteer design | completed
16 | 2019-05-23 | Unit Testing | completed
17 | 2019-05-24 | Review metting | completed
18 | 2019-05-25 | Saturday | holiday for him
19 | 2019-05-26 | Sunday | holiday for him
20 | 2019-05-27 | implementation of volunteer login and register screen and home page | completed
21 | 2019-05-28 | implementaion of user page | completed
22 | 2019-05-29 | implementaion of cards with posted data of food | completed
23 | 2019-05-30 | implementation of accept functionality | completed
24 | 2019-05-31 | Unit Testing | completed
25 | 2019-06-01 | Saturday | holiday for him
26 | 2019-06-02 | Sunday | holiday for him
27 | 2019-06-03 | implementation of profile and logout | completed
28 | 2019-06-04 | UI enhancemets and changes | completed
29 | 2019-06-05 | Rework on home page designing | completed
30 | 2019-06-06 | system testing | completed
31 | 2019-06-07 | system testing | completed
32 | 2019-06-08 | Saturday | holiday for him
33 | 2019-06-09 | Sunday | holiday for him
34 | 2019-06-10 | Report creation and documentaion | completed
35 | 2019-06-11 | Report creation and documentaion | completed
36 | 2019-06-12 | User acceptence Testing | completed